## Milestone Plan
Milestone | Nama Milestone | Minggu Ke- | Tanggal Mulai | Tanggal Selesai | Deliverable | Status | PIC | Progress | Catatan
M1 | Analisis & Perancangan Sistem | 1-2 | 2026-06-01 | 2026-06-12 | Dokumen PRD, SRS, Desain Sistem, Wireframe | Selesai | System Analyst | 100% | Dokumen sudah di-review stakeholder
M2 | Setup Proyek & UI Framework | 3-4 | 2026-06-15 | 2026-06-26 | Proyek React + Vite + Tailwind + Shadcn UI siap | Selesai | Frontend Lead | 100% | Boilerplate project selesai
M3 | Modul Authentication & RBAC | 4-5 | 2026-06-22 | 2026-07-03 | Login, logout, RBAC guard, route protection | Selesai | Frontend Dev | 100% | Integration dengan Firebase Auth
M4 | Modul Manajemen Siswa | 5-7 | 2026-06-29 | 2026-07-17 | CRUD siswa, pencarian, filter, detail siswa | Selesai | Frontend Dev | 100% | Termasuk responsive table
M5 | Modul Pelanggaran & Poin | 7-9 | 2026-07-13 | 2026-07-31 | CRUD pelanggaran, upload bukti, akumulasi poin otomatis | In Progress | Fullstack Dev | 75% | Integrasi dengan Cloud Functions
M6 | Modul Pembinaan & Tracking Kasus | 8-10 | 2026-07-20 | 2026-08-07 | Catatan pembinaan, konseling, timeline kasus, workflow status | In Progress | Fullstack Dev | 60% | Timeline component selesai
M7 | Modul Generator Surat | 9-11 | 2026-07-27 | 2026-08-14 | Generator SP1/SP2/SP3, Surat Perjanjian, Panggilan Ortu | In Progress | Frontend Dev | 40% | Template surat perlu finalisasi
M8 | Modul Notifikasi & Laporan | 10-12 | 2026-08-03 | 2026-08-21 | Notifikasi in-app + email, laporan + statistik | Not Started | Frontend Dev | 0% | Menunggu finalisasi threshold poin
M9 | Integrasi & Testing | 11-13 | 2026-08-10 | 2026-08-28 | Integrasi modul, unit test, RBAC test, performance test | Not Started | QA Lead | 0% | Test case sudah disiapkan
M10 | UAT & Deployment | 13-15 | 2026-08-24 | 2026-09-04 | User Acceptance Testing, deployment ke production | Not Started | Project Manager | 0% | Jadwal UAT dengan stakeholder
M11 | Go-Live & Dokumentasi | 15 | 2026-09-07 | 2026-09-11 | Aplikasi live, dokumentasi teknis, dokumentasi pengguna | Not Started | Project Manager | 0% | Persiapan maintenance plan